## ProjectTeam
Name | GitHub Alias | Role
Meier Jonathan | jntme | Scrum Master Sprint 1
Gfeller Sascha | gfels6 | Developer
Kyburz Philip | kybup1 | Developer
Ziegler Michaela | ziegm | Developer
Oda Jemal | Odaoj1 | Developer
Petitat Manuel | petim1 | Developer

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
0 | Miscellaneous | Differents tasks, that we can't allocate in the following stories or tasks which influences all other stories | high | 15 |  | 0 | waiting | waiting
1 | Login Health Visitor | The first step for an HealthVisitor is to LogIn in the WebApp. A Login window is appearing, where the HV can enter his credentials. If the login is successful, it opens the patient view (story 2). | medium | 15 |  | 0 | waiting | work in progress
2 | Patient Selector (List) | After the LogIn, the HV sees the complete list of all his patients. He can select a patient with clicking on its tab | medium | 15 |  | 0 | waiting | done
3 | Patient View | The core of the Application, the patient view is a semi-complete view of the patients personal data with a picture. The HV can look at their diagnosis and medication. There's a list of the goals as well. | high | 44 |  | 0 | waiting | cancelled
4 | Add/Change Objective | The HV can add or modify objectives in the patient view with clicking on a existing object or the "add" button. A new view is opening with the data of the objective. A progress bar is showing the actual state of the objective. The HV can complete an objective. | high | 20 |  | 0 | waiting
5 | Add/Change Activity | If an objective exists, the HV can add an activity entry in it. This activity has a name, description and also a progress bar. The HV can complete an activity. | high | 20 |  | 0 | waiting
6 | Add/Change Activity Record | For every activity, the HV can record one or more activity records. This activity record shows the process of one attempt. In this formular, the HV documents the status of the patient before and after the activity. He discuss and documents if the activity was successful or not with the patient together. This leads into an valuation of the record. | high | 30 |  | 0 | waiting
7 | Sprint Review Feedback | todo | medium | 15 |  |  | waiting
8 | Add/Change Notes | todo | medium | 8 |  |  | waiting
|  |  | TOTAL: | 182 | 0 | 0

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
0.1 | 1 | Create Persistance Manager | Create Persinstance Helper methods | DB Connect | jntme | kybup1 | high | 2 | 8 | 12 | finished
0.2 |  | Test-Server Set up |  | Server | [5 empty] | 0 | waiting
0.3 | 3 | Home button | Add a home button which leads back to SelectPatientView. | MVP | gfels6 | jntme | high | 4 | 3 | 3 | finished
0.4 | 2 | Navigation | Add Navigation in view so switch between different panes is possible. | View | jntme | gfels6 | high | 4 | 10 | 10 | finished
0.5 | 3 | Display ActivityList | Display the list of activities on the objective. | MVP | gfels6 | petim1 | high | 4 | 4 | 2.5 | finished
1.1 |  | Create User DB + Model |  | DB, Model | [5 empty] | 0 | waiting
1.2 |  | Check Credentials |  | Algorithm | [5 empty] | 0 | waiting
1.3 |  | VP Login |  | VP | [5 empty] | 0 | waiting
2.1 | 1 | Create Patient DB + Model | [5 empty] | -
2.1.1 | 1 | Create Patient DB | Create a project database and the relation patient. Create Java class from table | Database | petim1 | kybup1 | high | 5 | 3 | 3 | finished
2.1.2 | 1 | Create Patient Model | Create the Java patient model out of the DB | Model | jntme | gfels6 | high | 3 | 5 | 5 | finished
2.2 | 2 | VP Patient Selector | Show a list of patients of which one can be selected. | View, Presenter | gfels6 | jntme | low | 8 | 6 | 2 | finished
2.3 |  | Filter Patient for Health Visitor |  |  |  |  | low |  |  | 0 | waiting
3.1 | 1 | VP Patient | Main View Container and shows the patient data like name, birthdate etc. | Main Window | gfels6 | ziegm | medium | 9 | 11 | 12 | finished
3.2 | 1 | MVP Patient Info | [5 empty] | -
3.2.1 | 1 | M Patient Info | Creating a model for the Patient Info (may contain more informatino than just the patient model) | Model | jntme | gfels6 | high | 4 | 5 | 5 | finished
3.2.2 | 1 | V Patient Info | Creation of interface and view class wich shows advanced patient info | View | kybup1 | odaoj1 | medium | 4 | 4 | 7 | finished
3.2.3 | 1 | P Patient Info | Create the presenter for the Patient Info (acts between View Interface and Model) | Presenter | odaoj1 | jntme | medium | 3 | 3 | 3 | finished
3.2.4 | 2 | Bugfix PatientInfoView | At the moment the model can't be diplayed on the view. | View/Model | kybup1 | gfels6 | high | 6 | 6 | 6 | finished
3.2.4 | 2 | Bugfix PatientInfoView | At the moment the model can't be diplayed on the view. | View/Model | gfels6 | kybup1 | high | 6 | 6 | 6 | finished
3.2.5 | 2 | Bugfix ObjectiveList / NoteList | At the moment objects are not referenced to the containing list. | Model | jntme | kybup1 | high | 4 | 3 | 3 | finished
3.3 | 1 | Create Objective Model | Create Ojective and ObjectiveList Class and creating the corresponding relations in DB | Model, DB | kybup1 | petim1 | high | 5 | 5 | 5 | finished
3.4 | 1 | MVP Patient Objective List | Shows the objective (they can be created, opened or changed) | MVP | ziegm | jntme | medium | 9 | 9 | 7 | finished
3.4.1 | 2 | ObjectivePresenter | ObjectivePresenter so it can be opened and changed (on should not be able to open the activity yet) | View | ziegm | gfels6 | medium | 9 | 10 | 10 | pending
3.4.2 | 2 | ObjectiveView | Create the ObjectiveView and ist interface. | View | petim1 | ziegm | medium | 7 | 7 | 7 | finished
3.5 | 1 | Create Drug Model | Create the class model for drug in Java | Model | petim1 | ziegm | low | 4 | 4 | 5 | finished
3.6 | 1 | Create Diagnosis Model | Create the class for diagnosis in Java | Model | odaoj1 | petim1 | low | 6 | 6 | 5 | finished
3.7 | 2 | Change View of Diagnosis View | Diagnosis View should look the same as medication. | Model | odaoj1 | jntme | medium | 12 | 12 | 12 | finished
4.1 | 2 | Create Activity and ActivityList Model | Create the model for the activity concept. Includes Activity and ActivityList and testing on the patient. | Model | petim1 | ziegm | high | 5 | 5 | 6 | finished
4.2 | 3 | Modify Objective | The Objective should be editable. | MVP | jntme | ziegm | high | 3 | 3 | 3 | finished
4.3 | 3 | Create new Objective | Make it possible to create a new objective. | MVP | jntme | ziegm | high | 3 | 3 | 3 | finished
4.4 | 3 | Delete Objective | Make an object deletable. | MVP | jntme | ziegm | high | 2 | 4 | 4 | finished
5.1 | 3 | Activity View | Add the view of activity. | MVP | gfels6 | jntme | high | 3 | 3 | 4.5 | finished
5.2 | 3 | Create new ActivityRecord | Create a new ActivityRecord. | MVP | kybup1 | petim1 | high | 4 | 4 | 0 | pending
5.3 | 3 | Themeing | make sophobobia look nice | View | jntme | gfels6 | high | 4 | 4 | 0 | pending
| 3 | Themeing | make sophobobia look nice | View | gfels6 | jntme | high | 4 | 4 | 0 | pending
| 3 | Display ActivityRecordList | Display the list of ActivityRecords. | MVP | ziegm | petim1 | high | 4 | 4 | 4 | finished
6.1 | 3 | Create ActivityRecord Model | Create the model for ActivityRecord | Model | ziegm | petim1 | high | 2 | 3 | 3 | finished
6.2 | 3 | Persist in Model NOT in Presenter | Switch DB functions from presenter to model. | MP | jntme | gfels6 | high | 2 | 2 | 1 | finished
6.3 | 3 | Run and inspect FindBugs | Inspect bugs with FindBugs and try to fix them with the corresponding team member. | Reviewing | gfels6 | jntme | high | 3 | 3 | 1.5 | pending
6.4 | 3 | Breadcrumb Navigation | Add a breadcrumb navigation which shows the whole path for Patient -> Objective -> Activity -> ActivityRecord | MVP | gfels6 | kybup1 | low | 0 | 0 | 0 | waiting
7.1 | 2 | Buttons zu Icons | Buttons should get diplayed as icon instead of text and should be diplayed at the top of the view. | View | ziegm | gfels6 | medium | 3 | 2 | 2 | finished
7.2 | 2 | Addresse mit Button aufrufbar machen | Move address to modal dialog which can be opened with a button. | View | gfels6 | petim1 | medium | 2 | 3 | 3 | finished
7.3 | 2 | Fake Verlauf initiieren | Initialise Fake history | View | gfels6 | ziegm | medium | 1 | 1 | 1 | finished
7.4 | 2 | Fixing PatientView / Presenter | There are some misconcepts in PatientView and Presenter. | View | jntme | gfels6 | medium | 6 | 4 | 4 | finished
7.7 | 3 | Delete ActivityRecord | Make ActivityRecord deletable. | MVP | ziegm | petim1 | medium | 3 | 2 | 2 | finished
7.9 | 3 | Delete Activity | Make activity deletable. | MVP | petim1 | gfels6 | medium | 4 | 4 | 4 | finished
7.6 | 3 | Modify Activity | Make activity changeable. | MVP | jntme | odaoj1 | medium | 4 | 4 | 5 | finished
7.8 | 3 | Create Activity | Make it possible to create a new activity. | VP | jntme | jntme | high | 4 | 3.5 | 3.5 | finished
7.5 | 3 | Modify ActivityRecord | Make ActivityRecord changeable. | MVP | kybup1 | jntme | medium | 4 | 4 | 4 | finished
7.10 | 3 | implement Fake History | Implement the fake history as discussed on 22.12.17. | VP | odaoj1 | kybup1 | medium | 5 | 5 | 0 | finished
7.11 | 3 | Correction of Entries (to german and enter valid test data) | Change overall entries to german and enter new, valid test data. | MVP | petim1 | ziegm | high | 2 | 3 | 2.75 | pending
7.12 | 3 | Solve FindBugs & Write JUnitTests |  |  | ziegm |  | medium | 3 | 4 | 4 | finished
8.1 | 2 | NoteView, NotePresenter | Make it possible to add/open a note. | View, Presenter | kybup1 | jntme | high | 8 | 8 | 10 | finished
[8 empty] | planed h | updated h | actual h
|  |  |  | Ziel S1: 54h (je 9h) |  | Total Sprint 1: |  | 54 | 63 | 69
|  |  |  | Ziel S2: 72h (je 12h) |  | Total Sprint 2: |  | 81 | 83 | 82
|  |  |  | Ziel S3: 54h (je 9h) |  | Total Sprint 3: |  | 71 | 73.5 | 54.75
Effort Plan Original (h)
[8 empty] | gfels6 | ziegm | jntme | kybup1 | petim1 | odaoj1
[6 empty] | Total Sprint 1: |  | 9 | 9 | 9 | 9 | 9 | 9
[6 empty] | Total Sprint 2: |  | 17 | 12 | 14 | 14 | 12 | 12
[6 empty] | Total Sprint 3: |  | 18 | 12 | 22 | 8 | 6 | 5
Effort Plan Updated (h)
[8 empty] | gfels6 | ziegm | jntme | kybup1 | petim1 | odaoj1
[6 empty] | Total Sprint 1: |  | 11 | 9 | 18 | 9 | 7 | 9
[6 empty] | Total Sprint 2: |  | 16 | 12 | 17 | 14 | 12 | 12
[6 empty] | Total Sprint 3: |  | 17 | 13 | 23.5 | 8 | 7 | 5
Effort Actual (h)
[8 empty] | gfels6 | ziegm | jntme | kybup1 | petim1 | odaoj1
[6 empty] | Total Sprint 1: |  | 12 | 7 | 22 | 12 | 8 | 8
[6 empty] | Total Sprint 2: |  | 12 | 12 | 17 | 16 | 13 | 12
[6 empty] | Total Sprint 3: |  | 11.5 | 13 | 19.5 | 4 | 6.75 | 0

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources

## ScrumMeeting
Daily Scrum Meetings
Sprint | Datum | Beschreibung
1 | 2017-11-23 | Sprint 1 geplant, Tasks verteilt
1 | 2017-11-24 | Gemeinsam Projekt initiiert, mit DB begonnen, zusammen erste Projekte gelöst - we're set up! :)
1 | 2017-11-30 | Persistence Klasse soweit abgeschlossen
Patiene Model muss noch ganz fertig gemacht werden, kann aber bereits gelesen und in DB geschrieben werden
Main View beinahe fertig, wird noch gerezised, bis jetzt noch Dummywerte für Patient -> es muss noch ein richtiger Patient von der DB geholt werden
1 | 2017-12-01 | Momentan haben wir noch zwei Probleme, Model (Notes & Objectives) wird noch nicht ganz richtig gespeichert, Livedaten werden noch nicht richtig angezeigt.
2 | 2017-12-01 | Sprint 2 geplant, Tasks verteilt

## Sprint Review
Sprint Review 1
Datum | Inputs Product Owner
2017-12-01 | Buttons sollen in Icons umgewandelt werden statt mit Schrift
Adresse soll nicht immer angezeigt werden -> Designidee um das zu verstecken
Dashboard mit kurzen Infos: Dangernotes & Ziele
2017-12-22 | Model muss persistieren nicht der Presenter
Design ist nicht gerade der Bringer.